## GanttChart
Customer Database for Galactic Automotive
Jace Jikson
| Project Start Date | 2021-07-22 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
[9 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16
[9 empty] | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22
WBS | TASK |  | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Project Definition |  |  |  | - |  |  | -
1.1 | Define Tasks |  |  | 2021-07-22 | 2021-07-25 | 4 | 100% | 2 | bar: 2021-07-26
1.2 | Research on SRS |  |  | 2021-07-23 | 2021-07-27 | 5 | 100% | 3 | bar: 2021-07-28
1.3 | Research on IPO |  |  | 2021-07-26 | 2021-07-27 | 2 | 100% | 2 | bar: 2021-07-28
1.4 | Research on Gantt Chart |  |  | 2021-07-26 | 2021-07-26 | 1 | 100% | 1 | bar: 2021-07-27
1.5 | Project Timeline |  |  | 2021-07-26 | 2021-07-28 | 3 | 100% | 3 | bar: 2021-07-29
2 | Content Phase |  |  |  | - |  |  | -
2.1 | Gantt Chart |  |  | 2021-07-27 | 2021-08-02 | 7 | 100% | 5 | bar: 2021-08-03
2.2 | IPO Chart |  |  | 2021-07-26 | 2021-07-28 | 3 | 100% | 3
2.3 | Data Dictionary |  |  | 2021-07-29 | 2021-07-29 | 1 | 100% | 1
2.4 | SRS |  |  | 2021-08-01 | 2021-08-15 | 15 | 100% | 10 | bar: 2021-08-16
2.5 | Project Database |  |  | 2021-08-18 | 2021-08-27 | 10 | 0% | 8
3 | Design Phase |  |  |  | - |  |  | -
3.1 | Visual Basic Design |  |  | 2021-08-16 | 2021-08-20 | 5 | 0% | 5
3.2 | Application Formatting |  |  | 2021-08-21 | 2021-08-23 | 3 | 0% | 1
4 | Development Phase |  |  |  | - |  |  | -
4.1 | Develop in Visual Studio |  |  | 2021-08-22 | 2021-08-24 | 3 | 0% | 2
4.2 | Code the program |  |  | 2021-08-24 | 2021-08-28 | 5 | 0% | 4
4.3 | Link Database to the program |  |  | 2021-08-24 | 2021-08-24 | 1 | 0% | 1
4.4 | Finalise Application Interface |  |  | 2021-08-29 | 2021-08-29 | 1 | 0% | 0
5 | Review Phase |  |  |  | - |  |  | -
5.1 | Review SRS |  |  | 2021-08-29 | 2021-08-30 | 2 | 0% | 1
5.2 | Test Application |  |  | 2021-08-30 | 2021-08-30 | 1 | 0% | 1
5.3 | Finalise Data Dictionary, IPO chart and Gantt Chart |  |  | 2021-08-31 | 2021-08-31 | 1 | 0% | 1
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.